## Abstract
ABSTRACT OF ESCALATION BILLS
Name of work: ABC work
Agreement no.: -
Contractor: -
Employer / division: -
RPWA 100 clause 45. Base index: average of Oct-Dec 2025. Escalation = 0.75 × P × (I1 − I0) / I0 × R for each component.
Quarter-wise escalation (indices averaged over each calendar quarter)
No. | Quarter | Period |  | R - value of work in the quarter (₹) | Escalation (₹)
1 | Jan-Mar 2026 | 01.01.2026 to 31.03.2026
2 | Apr-Jun 2026 | 01.04.2026 to 30.06.2026
TOTAL
Bill-wise share of the quarterly escalation
No. | Bill | Period | Value of work done (₹) | Eligible value V (₹) | Escalation this bill (₹) | Up to previous bill (₹) | Cumulative (₹)
1 | RA bill 1 | 01.01.2026 to 31.01.2026 |  |  |  | 0
2 | Final bill (Final) (final) | 01.02.2026 to 14.04.2026
TOTAL
Blue figures in yellow cells (indices, weightages, values of work) are inputs; everything else is a formula.

## Bills
ESCALATION - BILL-WISE CALCULATION
Name of work: ABC work
Agreement no.: -
Contractor: -
Employer / division: -
Current index: Quarterly (CPWD 10CC, RPWA 100 clause 45): average of the 3 months of each calendar quarter; the bills are put to the quarters as set below.
Bill | Component / item | Weightage | Base index | Months (index used) | Current index | (I − I0) / I0 | Eligible value V (₹) | Escalation (₹) | Calculation (as worked out by the program)
RA bill 1 | Running account bill: 01.01.2026 to 31.01.2026
| Value of work done at agreement rates | [5 empty] | 2500000
| Less: extra / non-escalable items | [5 empty] | 0
| Less: materials issued by the department | [5 empty] | 0
Eligible value V
Escalation - RA bill 1 (share of the quarters, see Distribution)
Final bill (Final) | Final account bill: 01.02.2026 to 14.04.2026
| Value of work done at agreement rates | [5 empty] | 5000000
| Less: extra / non-escalable items | [5 empty] | 0
| Less: materials issued by the department | [5 empty] | 0
Eligible value V
Escalation - Final bill (Final) (share of the quarters, see Distribution)
* index frozen at the stipulated-completion month (lower of the two).

## Distribution
DISTRIBUTION OF THE BILLS TO THE QUARTERS
Name of work: ABC work
Agreement no.: -
Contractor: -
Employer / division: -
Each bill is taken in the quarter of its date of measurement (end of the bill period). Share of a bill in a quarter = V × days counted ÷ days of the bill period − deduction; days after the stipulated date 22.04.2026 are not counted; deduction = work up to ₹ 50,00,000.00 (value limit).
Quarter | Bill | Part from | Part to | Days of part | Days counted | Bill from | Bill to | Days of bill | Eligible value V (₹) | Deduction (₹) | Share in quarter (₹) | Escalation share (₹)
Jan-Mar 2026 | RA bill 1 | 2026-01-01 | 2026-01-31 |  |  | 2026-01-01 | 2026-01-31 |  |  | 0
Apr-Jun 2026 | Final bill (Final) | 2026-02-01 | 2026-04-14 |  |  | 2026-02-01 | 2026-04-14 |  |  | 0

## Quarters
ESCALATION - QUARTER-WISE CALCULATION
Name of work: ABC work
Agreement no.: -
Contractor: -
Employer / division: -
Index for a quarter = average of its three monthly indices. R = sum of the shares of the bills falling in the quarter (Distribution sheet). Escalation = R × weightage × (I − I0) / I0.
Quarter | Component | Weightage | Base index I0 | Months averaged | Quarter average I | (I − I0) / I0 | R (₹) | Escalation (₹) | Calculation (as worked out by the program)
Jan-Mar 2026 | 01.01.2026 to 31.03.2026
R - value of work done in the quarter
| Labour |  |  | Jan 2026, Feb 2026, Mar 2026 |  |  |  |  | I = (139.10 + 139.20 + 139.70) / 3 = 139.333; Labour = 0.75 × 33/100 × (139.333 − 138.100) / 138.100 × 25,00,000.00 = 5,525.89
| Material |  |  | Jan 2026, Feb 2026, Mar 2026 |  |  |  |  | I = (102.30 + 103.10 + 104.60) / 3 = 103.333; Material = 0.75 × 22/100 × (103.333 − 101.433) / 101.433 × 25,00,000.00 = 7,726.75
| H S Diesel / petrol |  |  | Jan 2026, Feb 2026, Mar 2026 |  |  |  |  | I = (83.40 + 84.30 + 89.80) / 3 = 85.833; H S Diesel / petrol = 0.75 × 4/100 × (85.833 − 84.667) / 84.667 × 25,00,000.00 = 1,033.46
| Cement |  |  | Jan 2026, Feb 2026, Mar 2026 |  |  |  |  | I = (93.40 + 93.40 + 94.20) / 3 = 93.667; Cement = 0.75 × 27/100 × (93.667 − 93.433) / 93.433 × 25,00,000.00 = 1,264.27
| Iron & steel |  |  | Jan 2026, Feb 2026, Mar 2026 |  |  |  |  | I = (84.40 + 86.90 + 88.70) / 3 = 86.667; Iron & steel = 0.75 × 4/100 × (86.667 − 79.233) / 79.233 × 25,00,000.00 = 7,036.18
| Bitumen |  |  | Jan 2026, Feb 2026, Mar 2026 |  |  |  |  | I = (102.60 + 102.50 + 105.00) / 3 = 103.367; Bitumen = 0.75 × 10/100 × (103.367 − 93.567) / 93.567 × 25,00,000.00 = 19,638.40
Escalation - Jan-Mar 2026
Apr-Jun 2026 | 01.04.2026 to 30.06.2026
R - value of work done in the quarter
| Labour |  |  | Apr 2026, May 2026, Jun 2026 |  |  |  |  | I = (139.70 + 141.50 + 142.80) / 3 = 141.333; Labour = 0.75 × 33/100 × (141.333 − 138.100) / 138.100 × 50,00,000.00 = 28,973.57
| Material |  |  | Apr 2026, May 2026, Jun 2026 |  |  |  |  | I = (108.90 + 110.10 + 110.30) / 3 = 109.767; Material = 0.75 × 22/100 × (109.767 − 101.433) / 101.433 × 50,00,000.00 = 67,778.51
| H S Diesel / petrol |  |  | Apr 2026, May 2026, Jun 2026 |  |  |  |  | I = (102.40 + 105.10 + 109.90) / 3 = 105.800; H S Diesel / petrol = 0.75 × 4/100 × (105.800 − 84.667) / 84.667 × 50,00,000.00 = 37,440.94
| Cement |  |  | Apr 2026, May 2026, Jun 2026 |  |  |  |  | I = (95.60 + 95.50 + 95.70) / 3 = 95.600; Cement = 0.75 × 27/100 × (95.600 − 93.433) / 93.433 × 50,00,000.00 = 23,479.31
| Iron & steel |  |  | Apr 2026, May 2026, Jun 2026 |  |  |  |  | I = (90.20 + 89.70 + 84.70) / 3 = 88.200; Iron & steel = 0.75 × 4/100 × (88.200 − 79.233) / 79.233 × 50,00,000.00 = 16,975.18
| Bitumen |  |  | Apr 2026, May 2026, Jun 2026 |  |  |  |  | I = (146.80 + 162.30 + 152.30) / 3 = 153.800; Bitumen = 0.75 × 10/100 × (153.800 − 93.567) / 93.567 × 50,00,000.00 = 2,41,405.42
Escalation - Apr-Jun 2026
* index frozen at the stipulated-completion month (lower of the two).

## Components
PRICE VARIATION COMPONENTS
Name of work: ABC work
Agreement no.: -
Contractor: -
Employer / division: -
Component | P (%) | Index series | Base index (average of Oct-Dec 2025)
Adjustable portion of R (clause 45) | 75% | -
Labour | 33% | CPI-IW Bhilwara (Labour Bureau, 2016=100)
Material | 22% | WPI All Commodities (OEA code 1000000000, 2022-23=100)
H S Diesel / petrol | 4% | WPI High Speed Diesel (HSD) (OEA code 1202010005, 2022-23=100)
Cement | 27% | WPI Manufacture of cement, lime and plaster (OEA code 1313050000, 2022-23=100)
Iron & steel | 4% | WPI Bars and Rods of Mild steel (OEA code 1314010014, 2022-23=100)
Bitumen | 10% | WPI Bitumen (OEA code 1202010007, 2022-23=100)
Total of P (must be 100 %)

## Indices
PRICE INDICES (monthly)
Name of work: ABC work
Agreement no.: -
Contractor: -
Employer / division: -
Published monthly indices (blue cells, editable). CPI-IW from the Labour Bureau index database (base 2016 = 100); WPI from the Office of the Economic Adviser.
Month | CPI-IW Bhilwara (Labour Bureau, 2016=100) | WPI All Commodities (OEA code 1000000000, 2022-23=100) | WPI High Speed Diesel (HSD) (OEA code 1202010005, 2022-23=100) | WPI Manufacture of cement, lime and plaster (OEA code 1313050000, 2022-23=100) | WPI Bars and Rods of Mild steel (OEA code 1314010014, 2022-23=100) | WPI Bitumen (OEA code 1202010007, 2022-23=100)
Oct 2025 (base) | 138 | 100.9 | 84.6 | 93.6 | 79.3 | 92.1
Nov 2025 (base) | 138 | 101.5 | 84.8 | 93.5 | 78.6 | 90.7
Dec 2025 (base) | 138.3 | 101.9 | 84.6 | 93.2 | 79.8 | 97.9
Jan 2026 | 139.1 | 102.3 | 83.4 | 93.4 | 84.4 | 102.6
Feb 2026 | 139.2 | 103.1 | 84.3 | 93.4 | 86.9 | 102.5
Mar 2026 | 139.7 | 104.6 | 89.8 | 94.2 | 88.7 | 105
Apr 2026 | 139.7 | 108.9 | 102.4 | 95.6 | 90.2 | 146.8
May 2026 | 141.5 | 110.1 | 105.1 | 95.5 | 89.7 | 162.3
Jun 2026 | 142.8 | 110.3 | 109.9 | 95.7 | 84.7 | 152.3